## Sheet1
RiskID | Description | Category | Likelihood | Impact | Owner | RequirementComplexity | AmbiguityScore | CodeChurn | ModuleComplexity | RevisionCount | RiskLevel
R001 | Ambiguous requirement for user authentication | Requirements | 4 | 3 | Sarah | 7 | 0.85 | 0 | 0 | 2 | High
R002 | Integration with external API may fail under high load | Technical | 3 | 4 | Ahmed | 5 | 0.3 | 40 | 9 | 3 | Medium
R003 | Inexperienced team with new framework | Resource | 2 | 4 | Maria | 0 | 0 | 0 | 0 | 0 | Medium
R004 | Server downtime risk during deployment | Operational | 3 | 5 | John | 0 | 0 | 10 | 7 | 0 | High
R005 | Missing input validation in payment module | Technical | 4 | 5 | Ali | 0 | 0 | 25 | 8 | 1 | High
R006 | Delay in client feedback cycles | Communication | 2 | 3 | Fatima | 0 | 0 | 0 | 0 | 0 | Low
R007 | Poor documentation may affect maintenance | Process | 3 | 2 | Omar | 3 | 0.4 | 0 | 0 | 4 | Low
R008 | Frequent changes in requirements | Requirements | 5 | 4 | Sara | 9 | 0.9 | 0 | 0 | 6 | High
R009 | Overlapping responsibilities between dev and QA | Organisational | 3 | 3 | Ahmed | 0 | 0 | 0 | 0 | 0 | Medium
R010 | Module with high churn and complexity | Technical | 4 | 4 | Aisha | 0 | 0 | 55 | 10 | 2 | High